## Project Plan
Deliverable | Sprint | Activity name | Date | Estimated (hr)
1. Design | Sprint #1 |  | Tues 8th Sept | 8
|  | Quiz Manager Project Planning |  | 1.5 | ✔️
|  | Business Requirement & Assumptions assessment |  | 2.5 | ✔️
|  | UI Design and Wireframes |  | 1.5 | ✔️
|  | Database Design and ERD |  | 1 | ✔️
|  | User Stories analysis |  | 1
|  | Establish Project Ways of Working |  | 0.5 | ✔️
2. Construction | Sprint #2 |  | Wed 9th Sept | 8
|  | Daily sprint planning |  | 0.25 | ✔️
|  | Daily product backlog grooming in Trello tickets |  | 0.25 | ✔️
|  | Project Infrastructure |  | 1.5
|  | Create application scaffold structure - laravel, auth, bootstrap |  |  | ✔️
|  | Set up database and configure with application |  |  | ✔️
|  | A user can login and log out |  | 4 | ✔️
Create users database table, model, factory, seeder, controller classes
Add automated tests
|  | A user can view the list of quizzes |  | 2 | ✔️
Create quiz database table, model, factory, seeder, controller classes
Create the blade webpage, http route, controller logic
| Sprint #3 |  | Thurs 10th Sept | 8.5
|  | Daily sprint planning |  | 0.25 | ✔️
|  | Daily product backlog grooming in Trello tickets |  | 0.25 | ✔️
A user can view the list of quizzes
|  | Add automated tests |  | 1 | ✔️
|  | A user can select a quiz and view the questions |  | 4 | ✔️
Create question database table, model, factory, seeder, controller classes
Create the blade webpage, http route, controller method
Handle foreign key logic
Add automated tests
|  | A user can view answers to questions |  | 3 | ✔️
Update view, handle javascript logic to show answers on click
|  | MVP 🎉 |  |  | 🎉
| Sprint #4 |  | Fri 11th Sept | 8.5
|  | Daily sprint planning |  | 0.25 | ✔️
|  | Daily product backlog grooming in Trello tickets |  | 0.25 | ✔️
|  | A restricted user can only see quiz questions |  | 2.5 | ✔️
|  | An edit user can add a quiz |  | 4 | ✔️
|  | An edit user can delete a quiz |  | 1.5 | ✔️
| Sprint #5 |  | Mon 14th Sept | 8.5
|  | Daily sprint planning |  | 0.25 | ✔️
|  | Daily product backlog grooming in Trello tickets |  | 0.25 | ✔️
|  | An edit user can add a question and its answers |  | 4 | ✔️
|  | An edit user can delete a question and answer |  | 4 | ✔️
| Sprint #6 |  | Tue 15th Sept | 8.5
|  | Daily sprint planning |  | 0.25 | ✔️
|  | Daily product backlog grooming in Trello tickets |  | 0.25 | ✔️
|  | An edit user can update a question or answer |  | 4 | ✔️
3. Testing |  | Testing documentation |  | 4
4. Documentation | Sprint #7 - FINAL SPRINT 😱 |  | Wed 16th Sept | 7.5
|  | Daily sprint planning |  | 0.25
|  | Daily product backlog grooming in Trello tickets |  | 0.25
|  | Evaluation |  | 2
|  | User Guide |  | 3
|  | Set Up instructions for Examiner |  | 2
Project Completion 🎉